## Sheet1
Sprint Number | ID | Story Priority | Story Status | Story Points | User Story
| GamePlay_1 | H | IP |  | Playing as a burger character, I want to be able to throw food like cheese, tomatoes, or use French fries as a weapon to be able to defeat my enemies or use them to be able to run away
| Animations_1 | H | IP |  | As a player, I should be able to move my character through the world so that I can progress through it and explore how I want to.
| GamePlay_4 | H | IP |  | As a player, I want to be able to fight against a variety of enemies so that I do not get bored with having to kill the same enemies repeatedly for the whole game.
| Graphics_1 | H | IP |  | As a player I want an environment to go through so that I can progress through the game.
| Animations_2 | H | IP |  | As a player I want my character to have animations so that the controls feel more realistic.
| User_Interface_1 | H | W |  | As a player, I need the interface for the game to clearly display important information such as health, lives, or score so that I can understand what is happening in the game and how I’m doing.
| GamePlay_2 | M | W |  | As a player, I want to be challenged while playing the game so that it does not seem boring or too easy.
| GamePlay_3 | M | W |  | As a player, I want to be rewarded for progressing through the game so that I have more motivation to continue playing it.
| GamePlay_6 | M | W |  | As a new player, I want to be able to view a tutorial or instructions on how to play, so that I can understand the game and so that I am not confused when I try to play it.
| GamePlay_5 | M | W |  | As a casual gamer, I want the game to be easy to pickup/understand because I want to be able to sit back and have fun without having to remember how to play the game and its mechanics.
| Dev_Metric_1 | M | W |  | As a developer, I want to be able to use a tool that lets me test any point in the game so that I do not have to waste my time going through things that come before the point I want to test.
| Dev_Metric_2 | M | W |  | As a developer, I want to be able to see player metric data, because after working hard on the game, I want to see how many people are enjoying the game.
| GamePlay_7 | M |  |  | As a player of modern video games, I would like the goal of the game to be clear.
| Menu_Option_1 | L | IP |  | As a player with specific preferences, I want to be able to have options that allow me to customize things like controls, volume, or graphics so that I can adjust the game to suit my preferences.
| Save_1 | L | W |  | As a player who does not have a lot of time to play video games, I want to be able to save my current game state at any time so that I can resume later from when it was last saved
| Save_2 | L | W |  | As a player I want there to be a button dedicated to pausing the game.
| Graphics_2 | L | W |  | As a player of modern video games, I would like the gameplay to be visually appealing and unambiguous so that will make the game feel polished and complete
| Sound_1 | L | W |  | As someone who enjoys music, I would like for the game to have complete sound design, from sound effects that enhance realism to pleasant music, which keeps a game from feeling dull.
| Menu_Option_1 | L | W |  | As a player I want sound options to be configurable because sometimes I want to play with music, other times without.
| User_Interface_2 | L | W |  | As a competitive player, I would like to save high-scores or achievements of some kind so that I and others may compete against those scores.
| Save_3 | L | W |  | As a player who is frequently interrupted, I want to be able to pause the game, so that I do not get killed or lose points when I must focus on something other than the game for a short time.
| GamePlay_6 | L | W |  | As a user with limited data, I need the game to be playable offline because I am not always in an area with Wi-Fi and using mobile data can get expensive.
| Menu_Option_1 | L | W |  | As a player, I need the game to have subtitles. I prefer to be able to both listen to and read the game dialog as I take in the information better this way.
| Menu_Option_1 | L | W |  | As a colorblind player, I need the game to have a colorblind mode because otherwise, I am not able to distinguish many game objects rendering the game quite frustrating.

## Sheet2 (2) (hidden)
Sprint Number | Sprint Goal | Member Name and % completed | Story Type | Story Points | Story Points Completed | User Story
1 |  | Michael Rumohr |  |  |  | As a player I want an environment to go through so that I can progress through the game.
1 |  | Michael Taylor |  |  |  | As a player I want my character to have animations so that the controls feel more realistic.
1 |  | Ethan Esber |  |  |  | As a player I want an enemy to go against me so that I feel more challenged.
1 |  | Kevin Finley |  |  |  | As a player I want to be able to shoot food so that I can defeat my enemies.
1 |  | Cooper Dahlberg |  |  |  | As a player I want configurable controls so that I can better customize my gameplay to my style.
1 |  | David Sincyr |  |  |  | As a player I want to have a character that I can control so that I can move through the world.
take out ones not being worked on!!!!!!!
Playing as a burger character, I want to be able to throw food like cheese, tomatoes, or use French fries as a weapon to be able to defeat my enemies or use them to be able to run away
As a player, I should be able to move my character through the world so that I can progress through it and explore how I want to.
As a player, I want to be able to fight against a variety of enemies so that I do not get bored with having to kill the same enemies repeatedly for the whole game.
As a player I want an environment to go through so that I can progress through the game.
As a player I want my character to have animations so that the controls feel more realistic.
As a player, I need the interface for the game to clearly display important information such as health, lives, or score so that I can understand what is happening in the game and how I’m doing.
As a player, I want to be challenged while playing the game so that it does not seem boring or too easy.
As a player, I want to be rewarded for progressing through the game so that I have more motivation to continue playing it.
As a new player, I want to be able to view a tutorial or instructions on how to play, so that I can understand the game and so that I am not confused when I try to play it.
As a casual gamer, I want the game to be easy to pickup/understand because I want to be able to sit back and have fun without having to remember how to play the game and its mechanics.
As a developer, I want to be able to use a tool that lets me test any point in the game so that I do not have to waste my time going through things that come before the point I want to test.
As a developer, I want to be able to see player metric data, because after working hard on the game, I want to see how many people are enjoying the game.
As a player of modern video games, I would like the goal of the game to be clear.
As a player with specific preferences, I want to be able to have options that allow me to customize things like controls, volume, or graphics so that I can adjust the game to suit my preferences.
As a player who does not have a lot of time to play video games, I want to be able to save my current game state at any time so that I can resume later from when it was last saved
As a player I want there to be a button dedicated to pausing the game.
As a player of modern video games, I would like the gameplay to be visually appealing and unambiguous so that will make the game feel polished and complete
As someone who enjoys music, I would like for the game to have complete sound design, from sound effects that enhance realism to pleasant music, which keeps a game from feeling dull.
As a player I want sound options to be configurable because sometimes I want to play with music, other times without.
As a competitive player, I would like to save high-scores or achievements of some kind so that I and others may compete against those scores.
As a player who is frequently interrupted, I want to be able to pause the game, so that I do not get killed or lose points when I must focus on something other than the game for a short time.
As a user with limited data, I need the game to be playable offline because I am not always in an area with Wi-Fi and using mobile data can get expensive.
As a player, I need the game to have subtitles. I prefer to be able to both listen to and read the game dialog as I take in the information better this way.
As a colorblind player, I need the game to have a colorblind mode because otherwise, I am not able to distinguish many game objects rendering the game quite frustrating.

## Sheet2
Sprint Number | Sprint Goal | Member Name and % completed | Story Type | Story Points | Story Points Completed | User Story
1 | 5 | Michael Rumohr | F | 5 | 3 | As a player I want an environment to go through so that I can progress through the game.
1 | 4 | Michael Taylor | F | 13 | 13 | As a player I want my character to have animations so that the controls feel more realistic.
3 | 5 | Ethan Esber | F | 5 | 3 | As a player I want an environment to go through so that I can progress through the game
4 | 4 | Kevin Finley 100% | F | 5 | 5 | As a player I want to be able to pick up items so that I can use them.
4 | 5 | Kevin Finley | F | 8 | 3 | As a player I want to be able to use the items I pick up so that I can gain power ups.
4 | 4 | Michael Taylor | F | 5 | 2 | As a player I want to be able to exit the game so that I can pick it up at another time.
4 | 4 | Michael Taylor | F | 13 | 3 | As a player I want to be able to load my previously saved game so that I can continue where I left off.
4 | 4 | Michael Taylor | F | 2 | 1 | As a player who does not have a lot of time to play video games, I want to be able to save my current game state at any time so that I can resume later from when it was last saved
4 | 5 | David Sincyr | F | 5 | 3 | As a player, I want to be able to fight against a variety of enemies so that I do not get bored with having to kill the same enemies repeatedly for the whole game.
4 | 5 | Cooper Dahlberg | F | 5 | 2 | As a player I want to be able to lose lives so that the game has risks in it.
4 | 5 | Cooper Dahlberg | F | 5 | 2 | As a player I want to be able to get a gameover so that I can lose the game.
take out ones not being worked on!!!!!!!
Playing as a burger character, I want to be able to throw food like cheese, tomatoes, or use French fries as a weapon to be able to defeat my enemies or use them to be able to run away
As a player, I should be able to move my character through the world so that I can progress through it and explore how I want to.
As a player, I want to be able to fight against a variety of enemies so that I do not get bored with having to kill the same enemies repeatedly for the whole game.
As a player I want an environment to go through so that I can progress through the game.
As a player I want my character to have animations so that the controls feel more realistic.
As a player, I need the interface for the game to clearly display important information such as health, lives, or score so that I can understand what is happening in the game and how I’m doing.
As a player, I want to be challenged while playing the game so that it does not seem boring or too easy.
As a player, I want to be rewarded for progressing through the game so that I have more motivation to continue playing it.
As a new player, I want to be able to view a tutorial or instructions on how to play, so that I can understand the game and so that I am not confused when I try to play it.
As a casual gamer, I want the game to be easy to pickup/understand because I want to be able to sit back and have fun without having to remember how to play the game and its mechanics.
As a developer, I want to be able to use a tool that lets me test any point in the game so that I do not have to waste my time going through things that come before the point I want to test.
As a developer, I want to be able to see player metric data, because after working hard on the game, I want to see how many people are enjoying the game.
As a player of modern video games, I would like the goal of the game to be clear.
As a player with specific preferences, I want to be able to have options that allow me to customize things like controls, volume, or graphics so that I can adjust the game to suit my preferences.
As a player who does not have a lot of time to play video games, I want to be able to save my current game state at any time so that I can resume later from when it was last saved
As a player I want there to be a button dedicated to pausing the game.
As a player of modern video games, I would like the gameplay to be visually appealing and unambiguous so that will make the game feel polished and complete
As someone who enjoys music, I would like for the game to have complete sound design, from sound effects that enhance realism to pleasant music, which keeps a game from feeling dull.
As a player I want sound options to be configurable because sometimes I want to play with music, other times without.
As a competitive player, I would like to save high-scores or achievements of some kind so that I and others may compete against those scores.
As a player who is frequently interrupted, I want to be able to pause the game, so that I do not get killed or lose points when I must focus on something other than the game for a short time.
As a user with limited data, I need the game to be playable offline because I am not always in an area with Wi-Fi and using mobile data can get expensive.
As a player, I need the game to have subtitles. I prefer to be able to both listen to and read the game dialog as I take in the information better this way.
As a colorblind player, I need the game to have a colorblind mode because otherwise, I am not able to distinguish many game objects rendering the game quite frustrating.